## 6 Day Forecast
| Project name: |  |  | AB123 |  |  | 6 DAY LOOKAHEAD
|  |  | Project start date: | 2015-02-19
2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02
42054.0001 |  |  | 42055.0001 |  |  | 42056.0001 |  |  | 42057.0001 | RIH 5" HWDP to ± 575 ft |  | 42058.0001 |  |  | 42059.0001 |  |  | 42060.0001 |  |  | 42061.0001 |  |  | 42062.0001 |  |  | 42063.0001 |  |  | 42064.0001 |  |  | 42065.0001 | B/R OOH Shuaiba from 5,866 ft to 4,075 ft 20 mins/std
42054.0418 |  |  | 42055.0418 |  |  | 42056.0418 |  |  | 42057.0418 | Gyro data take check shot survey. SDC take one gyro single shot survey |  | 42058.0418 | Drill 16" hole to ± 2,837 ft |  | 42059.0418 |  |  | 42060.0418 |  |  | 42061.0418 |  |  | 42062.0418 | POOH |  | 42063.0418 |  |  | 42064.0418 |  |  | 42065.0418
42054.0834 |  |  | 42055.0834 |  |  | 42056.0834 | N/U bell nipple |  | 42057.0834 |  |  | 42058.0834 |  |  | 42059.0834 | Pump sweeps, Circ hole clean |  | 42060.0834 |  |  | 42061.0834 | Heavy lift - N/U HP riser & BOP's |  | 42062.0834 |  |  | 42063.0834 |  |  | 42064.0834 |  |  | 42065.0834
42054.1251 |  |  | 42055.1251 |  |  | 42056.1251 | N/u flood line |  | 42057.1251 | Clean out conductor to 593 ft |  | 42058.1251 |  |  | 42059.1251 | B/R OOH to ± 1,800 ft |  | 42060.1251 |  |  | 42061.1251 |  |  | 42062.1251 |  |  | 42063.1251 |  |  | 42064.1251 |  |  | 42065.1251
42054.1668 |  |  | 42055.1668 | Heavy lift - Install XMT |  | 42056.1668 | M/U 17" Bit , Bit sub. RIH with clean out BHA |  | 42057.1668 | Drill 16" hole to ± 1,400 ft |  | 42058.1668 |  |  | 42059.1668 |  |  | 42060.1668 | P/U CSS hgr and RIH to ± 2,837 ft |  | 42061.1668 |  |  | 42062.1668 |  |  | 42063.1668 |  |  | 42064.1668 |  |  | 42065.1668
42054.2084 |  |  | 42055.2084 |  |  | 42056.2084 |  |  | 42057.2084 |  |  | 42058.2084 |  |  | 42059.2084 |  |  | 42060.2084 | L/D upper bell nipple |  | 42061.2084 |  |  | 42062.2084 | Lay out 8" OD BHA |  | 42063.2084 |  |  | 42064.2084 |  |  | 42065.2084
42054.2501 |  |  | 42055.2501 |  |  | 42056.2501 | Clean out conductor to 573 ft. POOH. |  | 42057.2501 |  |  | 42058.2501 |  |  | 42059.2501 |  |  | 42060.2501 |  |  | 42061.2501 |  |  | 42062.2501 |  |  | 42063.2501 |  |  | 42064.2501 |  |  | 42065.2501
42054.2918 |  |  | 42055.2918 |  |  | 42056.2918 |  |  | 42057.2918 |  |  | 42058.2918 |  |  | 42059.2918 | RIH to bottom |  | 42060.2918 | R/U cmt head & surface lines |  | 42061.2918 |  |  | 42062.2918 |  |  | 42063.2918 |  |  | 42064.2918 |  |  | 42065.2918
42054.3334 |  |  | 42055.3334 | P/T XMT void, hgr neck seal & body |  | 42056.3334 |  |  | 42057.3334 |  |  | 42058.3334 |  |  | 42059.3334 |  |  | 42060.3334 | Cement 1st Stage |  | 42061.3334 | Function test BOP's, install bell nipple |  | 42062.3334 |  |  | 42063.3334 |  |  | 42064.3334 |  |  | 42065.3334
42054.3751 |  |  | 42055.3751 |  |  | 42056.3751 |  |  | 42057.3751 |  |  | 42058.3751 |  |  | 42059.3751 | Pump sweeps, Spot KCl pill |  | 42060.3751 |  |  | 42061.3751 | Test well against ISR blind shear to 2,000psi |  | 42062.3751 | Rig Up SDC |  | 42063.3751 |  |  | 42064.3751 |  |  | 42065.3751
42054.4168 | #N/A |  | 42055.4168 |  |  | 42056.4168 | R/U and run 20" centroller gyro |  | 42057.4168 |  |  | 42058.4168 |  |  | 42059.4168 | POOH to surface |  | 42060.4168 | Displace cement, P/T 2,000 psi, check floats. |  | 42061.4168 | Install W/B |  | 42062.4168 | Run 13-3/8" centroller gyro |  | 42063.4168 |  |  | 42064.4168 |  |  | 42065.4168
42054.4584 | Shear GLV, inflow test GLV |  | 42055.4584 | R/U Sline & PCE, ret. CRQ/DBSS, R/D S/L & PCE |  | 42056.4584 |  |  | 42057.4584 |  |  | 42058.4584 |  |  | 42059.4584 |  |  | 42060.4584 | Lift diverter and LP riser ± 3 ft |  | 42061.4584 | Lay out 16" BHA from derrick |  | 42062.4584 |  |  | 42063.4584 |  |  | 42064.4584 | Flow chk, change gear Hi, TD survey |  | 42065.4584
42054.5001 | R/U Sline, install CRQ/DBSS, P/T, R/D Sline |  | 42055.5001 |  |  | 42056.5001 | Slip and cut D/L. Change out Martin decker. Replace saversub |  | 42057.5001 |  |  | 42058.5001 |  |  | 42059.5001 |  |  | 42060.5001 | Drop opening bomb, open DV collar |  | 42061.5001 | M/U 12-1/4" cleanout BHA and RIH to +/- 376 ft |  | 42062.5001 |  |  | 42063.5001 |  |  | 42064.5001 | B/R OOH Hawar 7,179 ft to 5,866 ft 40 mins/std |  | 42065.5001 | B/R OOH NU from 4,075 ft to 3638 ft 40 mins/std
42054.5418 |  |  | 42055.5418 |  |  | 42056.5418 |  |  | 42057.5418 |  |  | 42058.5418 |  |  | 42059.5418 |  |  | 42060.5418 | Cement 2nd Stage. Displace closing plug to stage collar. |  | 42061.5418 |  |  | 42062.5418 | Rig down |  | 42063.5418 |  |  | 42064.5418 |  |  | 42065.5418
42054.5834 |  |  | 42055.5834 |  |  | 42056.5834 |  |  | 42057.5834 |  |  | 42058.5834 |  |  | 42059.5834 |  |  | 42060.5834 |  |  | 42061.5834 | RIH and tag Closing plug at 571 ft |  | 42062.5834 | P/U & M/U 12-1/4" PDC Xceed BHA |  | 42063.5834 |  |  | 42064.5834 |  |  | 42065.5834
42054.6251 |  |  | 42055.6251 | Shear chem inj sub. Pump 30 bbls via LVO. |  | 42056.6251 |  |  | 42057.6251 |  |  | 42058.6251 |  |  | 42059.6251 | R/B 16" BHA |  | 42060.6251 | R/D cmt head |  | 42061.6251 | Drill out DV collar/ plugs |  | 42062.6251 |  |  | 42063.6251 |  |  | 42064.6251 |  |  | 42065.6251
42054.6668 | L/D 7" landing string, clear RF |  | 42055.6668 |  |  | 42056.6668 | P/U & M/U 16" RSS BHA |  | 42057.6668 |  |  | 42058.6668 |  |  | 42059.6668 |  |  | 42060.6668 | Cut 13-3/8" csg @ 73" above TOS |  | 42061.6668 |  |  | 42062.6668 |  |  | 42063.6668 |  |  | 42064.6668 |  |  | 42065.6668
42054.7084 | Heavy Lift - N/D Bell Nipple, BOP & Riser |  | 42055.7084 | Depressurize X-mas tree and prepare for skidding operations |  | 42056.7084 |  |  | 42057.7084 |  |  | 42058.7084 |  |  | 42059.7084 |  |  | 42060.7084 |  |  | 42061.7084 | RIH 12-1/4" BHA to +/- 2,787 ft |  | 42062.7084 |  |  | 42063.7084 |  |  | 42064.7084 |  |  | 42065.7084
42054.7501 |  |  | 42055.7501 | Skid to WELL abc, Secure rig |  | 42056.7501 |  |  | 42057.7501 | Spot pill, POOH |  | 42058.7501 |  |  | 42059.7501 | R/U csg equipment |  | 42060.7501 | L/D 13-3/8" csg stump, R/D handling eqpt |  | 42061.7501 |  |  | 42062.7501 | RIH on 5" DP to ± 1,600 ft |  | 42063.7501 |  |  | 42064.7501 |  |  | 42065.7501
42054.7918 |  |  | 42055.7918 |  |  | 42056.7918 |  |  | 42057.7918 |  |  | 42058.7918 |  |  | 42059.7918 |  |  | 42060.7918 |  |  | 42061.7918 | Drill out plugs, baffle, shoe track cement and shoe |  | 42062.7918 | Shallow test tools |  | 42063.7918 |  |  | 42064.7918 |  |  | 42065.7918
42054.8334 |  |  | 42055.8334 | Perform DROPS survey & install roller |  | 42056.8334 |  |  | 42057.8334 | L/D Motor |  | 42058.8334 |  |  | 42059.8334 | RIH 13-3/8" casing to ± 2,250 ft |  | 42060.8334 | Heavy lift - N/D diverter & LP riser |  | 42061.8334 |  |  | 42062.8334 | RIH to 2,847 ft . Downlink Xceed |  | 42063.8334 |  |  | 42064.8334 |  |  | 42065.8334 | B/R OOH from 3,638 ft to 3,170 ft 20 mins/std
42054.8751 |  |  | 42055.8751 |  |  | 42056.8751 |  |  | 42057.8751 | P/U & M/U PD1100 BHA |  | 42058.8751 |  |  | 42059.8751 |  |  | 42060.8751 |  |  | 42061.8751 | Drill out 10 ft of new formation to 2,847 ft . C&C mud. |  | 42062.8751 | Drill 12-1/4" hole from 2,847 ft to 7,179 ft |  | 42063.8751 |  |  | 42064.8751 |  |  | 42065.8751
42054.9168 | Remove comms, term. C/L's, install hgr neck seal |  | 42055.9168 | Heavy Lift - Install LP Riser |  | 42056.9168 |  |  | 42057.9168 |  |  | 42058.9168 |  |  | 42059.9168 |  |  | 42060.9168 | Heavy lift - N/U & P/T WH |  | 42061.9168 |  |  | 42062.9168 |  |  | 42063.9168 |  |  | 42064.9168 |  |  | 42065.9168
42054.9584 |  |  | 42055.9584 | N/U diverter |  | 42056.9584 | Shallow pulse test MWD |  | 42057.9584 | Wiper trip. RIH with PD1100 to 1,400 ft |  | 42058.9584 |  |  | 42059.9584 |  |  | 42060.9584 |  |  | 42061.9584 |  |  | 42062.9584 |  |  | 42063.9584 |  |  | 42064.9584 |  |  | 42065.9584
EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG
EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG
Drill H2O |  |  | XX-MR-01 Casing & Accessories |  |  | Drillwater 200 MT (Kehoe Tide) | [23 empty] | GD02 CMR-03 12-1/2" Mud Chems
Bentonite 30MT |  |  | MR-01-DQ WH | [8 empty] | 12 1/4"Mud Chem(CMR-05) |  |  | 12 1/4"Mud Chem(CMR-06) |  |  | 12 1/4"Mud Chem(CMR-07) |  |  | 9-5/8" Casing (MR # 4)
|  |  | MR-01 - Hall cement head |  |  | BAD WEATHER |  |  | BAD WEATHER | [8 empty] | 12-1/4" RSS BHA (MR 05) |  |  | 60 MT Elasticem cement (CMR 09) |  |  | 9-5/8" cementing chemicals (CMR 08) | [5 empty] | 170 JOINTS 5" DP (MR 06)
[12 empty] | BAD WEATHER | [11 empty] | Elasticem cement (CMR 09)
TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM
15 | Shelf | 14 |  | HLB Evo trieve |  | 2 | Baker e-Line |  | 1 | Mud engr | 1 | 3 | AL Masaood |  | 1 | New Medic(Shelf) |  | 1 | Data Engr.(Weatherford) | 1 | 11 | Shelf C/C | 12 |  |  |  | 1 | Data Engr.(Wfd) | 1 |  |  |  | 6 | Al-Masood
2 | SLB D&M |  |  |  |  | 1 | Campboss(Teyseer) | 1 |  | Baker e-Line | 2 |  | (above booking confirmed) |  | 1 | James Granger |  |  | (above booking confirmed) |  | 1 | WSG(MITAS) | [5 empty] | SDC | 2 |  |  |  |  | (above booking confirmed)
2 | Gyrodata |  |  | Al Masaood |  | 1 | Cementer(Hall) |  |  | WSS | 1 |  |  |  | 1 | Ian |  |  |  |  | 1 | Ian(RSTC) | [5 empty] | (above booking confirmed)
| Aggreko(Shelf) | 1 |  | Drill Qup |  |  | rstc(IAN) | 1 | 1 | Halliburton (CMT helper) |  |  | NOV Centrifuge engineer | 1 |  | (above booking confirmed) | [5 empty] | James Granger | 1
5 | Bernd DSV | 1 |  | NOV ( RA change out) |  |  | SLB S/line | 2 |  | Cementer | 1 | [10 empty] | (above booking confirmed)
| (above booking confirmed) |  | 4 | Painters |  |  | HLB Evo trieve | 2 |  | Teyseer(cook) | 1 |  |  |  |  | Gyrodata | 2 | [13 empty] | (No Seats Available)
|  |  |  | (above booking confirmed) |  |  | WSS | 1 |  | (above booking confirmed) | [7 empty] | 1 | NOV centrifuge engineer |  | 2 | MOQ Geologist
[7 empty] | Drill Quip | 3 | [9 empty] | 1 | WSE (Kevin Pearce) |  |  | Al-Masood | 5
[7 empty] | (above booking confirmed) | [13 empty] | 2 | Weatherford sample catchers
[22 empty] | DQ Engineer | 2
24 |  | 16 | 4 |  | 0 | 4 |  | 10 | 2 |  | 6 | 3 |  | 1 | 3 |  | 2 | 3 |  | 1 | 17 |  | 20 | 0 |  | 0 | 1 |  | 3 | 0 |  | 0 | 6 |  | 0
POB |  | 106 | POB |  | 110 | POB |  | 104 | POB |  | 100 | POB |  | 102 | POB |  | 103 | POB |  | 105 | POB |  | 102 | POB |  | 102 | POB |  | 100 | POB |  | 100 | POB |  | 106
AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB |  |  | AOB
2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02
............................................................................................................................
Formulas:
EQUIPMENT FROM RIG = [EQUIPMENT FROM RIG]+1

## Logistics
| 2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02 |  |  | 2015-03-03 |  |  | 2015-03-04 |  |  | 2015-03-05 |  |  | 2015-03-06 |  |  | 2015-03-07 |  |  | 2015-03-08 |  |  | 2015-03-09 |  |  | 2015-03-10 |  |  | 2015-03-11 |  |  | 2015-03-12 |  |  | 2015-03-13 |  |  | 2015-03-14 |  |  | 2015-03-15 |  |  | 2015-03-16 |  |  | 2015-03-17 |  |  | 2015-03-18 |  |  | 2015-03-19 |  |  | 2015-03-20 |  |  | 2015-03-21 |  |  | 2015-03-22 |  |  | 2015-03-23 |  |  | 2015-03-24 |  |  | 2015-03-25 |  |  | 2015-03-26 |  |  | 2015-03-27 |  |  | 2015-03-28 |  |  | 2015-03-29 |  |  | 2015-03-30 |  |  | 2015-03-31 |  |  | 2015-04-01 |  |  | 2015-04-02
|  |  | 2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02 |  |  | 2015-03-03 |  |  | 2015-03-04 |  |  | 2015-03-05 |  |  | 2015-03-06 |  |  | 2015-03-07 |  |  | 2015-03-08 |  |  | 2015-03-09 |  |  | 2015-03-10 |  |  | 2015-03-11 |  |  | 2015-03-12 |  |  | 2015-03-13 |  |  | 2015-03-14 |  |  | 2015-03-15 |  |  | 2015-03-16 |  |  | 2015-03-17 |  |  | 2015-03-18 |  |  | 2015-03-19 |  |  | 2015-03-20 |  |  | 2015-03-21 |  |  | 2015-03-22 |  |  | 2015-03-23 |  |  | 2015-03-24 |  |  | 2015-03-25 |  |  | 2015-03-26 |  |  | 2015-03-27 |  |  | 2015-03-28 |  |  | 2015-03-29 |  |  | 2015-03-30 |  |  | 2015-03-31 |  |  | 2015-04-01 |  |  | 2015-04-02
|  | 2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02 |  |  | 2015-03-03 |  |  | 2015-03-04 |  |  | 2015-03-05 |  |  | 2015-03-06 |  |  | 2015-03-07 |  |  | 2015-03-08 |  |  | 2015-03-09 |  |  | 2015-03-10 |  |  | 2015-03-11 |  |  | 2015-03-12 |  |  | 2015-03-13 |  |  | 2015-03-14 |  |  | 2015-03-15 |  |  | 2015-03-16 |  |  | 2015-03-17 |  |  | 2015-03-18 |  |  | 2015-03-19 |  |  | 2015-03-20 |  |  | 2015-03-21 |  |  | 2015-03-22 |  |  | 2015-03-23 |  |  | 2015-03-24 |  |  | 2015-03-25 |  |  | 2015-03-26 |  |  | 2015-03-27 |  |  | 2015-03-28 |  |  | 2015-03-29 |  |  | 2015-03-30 |  |  | 2015-03-31 |  |  | 2015-04-01 |  |  | 2015-04-02
| 2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02 |  |  | 2015-03-03 |  |  | 2015-03-04 |  |  | 2015-03-05 |  |  | 2015-03-06 |  |  | 2015-03-07 |  |  | 2015-03-08 |  |  | 2015-03-09 |  |  | 2015-03-10 |  |  | 2015-03-11 |  |  | 2015-03-12 |  |  | 2015-03-13 |  |  | 2015-03-14 |  |  | 2015-03-15 |  |  | 2015-03-16 |  |  | 2015-03-17 |  |  | 2015-03-18 |  |  | 2015-03-19 |  |  | 2015-03-20 |  |  | 2015-03-21 |  |  | 2015-03-22 |  |  | 2015-03-23 |  |  | 2015-03-24 |  |  | 2015-03-25 |  |  | 2015-03-26 |  |  | 2015-03-27 |  |  | 2015-03-28 |  |  | 2015-03-29 |  |  | 2015-03-30 |  |  | 2015-03-31 |  |  | 2015-04-01 |  |  | 2015-04-02
| 42054 |  |  | 42055.0001 |  |  | 42056.0001 |  |  | 42057.0001 | RIH 5" HWDP to ± 575 ft |  | 42058.0001 |  |  | 42059.0001 |  |  | 42060.0001 |  |  | 42061.0001 |  |  | 42062.0001 |  |  | 42063.0001 |  |  | 42064.0001 |  |  | 42065.0001 | B/R OOH Shuaiba from 5,866 ft to 4,075 ft 20 mins/std |  | 42066.0001 |  |  | 42067.0001 | M/U 9-5/8" shoetrack |  | 42068.0001 | Mix & pump cement |  | 42069.0001 |  |  | 42070.0001 | M/U 8-1/2" BHA (Xceed 675 /Tele-/Stethp/Ecoscope) |  | 42071.0001 |  |  | 42072.0001 |  |  | 42073.0001 |  |  | 42074.0001 |  |  | 42075.0001 |  |  | 42076.0001 |  |  | 42077.0001 |  |  | 42078.0001 |  |  | 42079.0001 |  |  | 42080.0001 |  |  | 42081.0001 | P/U Baker PBR and RIH |  | 42082.0001 |  |  | 42083.0001 |  |  | 42084.0001 | L/O Liner # 3 running tool |  | 42085.0001 |  |  | 42086.0001 |  |  | 42087.0001 |  |  | 42088.0001 | P/U & M/U ROC, LVO, X/O, HS-IVC |  | 42089.0001 |  |  | 42090.0001 |  |  | 42091.0001 | Shear GLV, inflow test GLV |  | 42092.0001 | R/U Sline & PCE, retrieve CRQ/DBSS, R/D Sline & PCE |  | 42093.0001 |  |  | 42094.0001 |  |  | 42095.0001 |  |  | 42096.0001
| 42054.0417 |  |  | 42055.0418 |  |  | 42056.0418 |  |  | 42057.0418 | Gyro data take check shot survey. SDC take one gyro single shot survey |  | 42058.0418 | Drill 16" hole to ± 2,837 ft |  | 42059.0418 |  |  | 42060.0418 |  |  | 42061.0418 |  |  | 42062.0418 | POOH |  | 42063.0418 |  |  | 42064.0418 |  |  | 42065.0418 |  |  | 42066.0418 | B/R OOH from 3,170 ft to shoe at 2,837 ft at 30 mins/std |  | 42067.0418 | RIH 9-5/8" csg to 7,169 ft |  | 42068.0418 |  |  | 42069.0418 |  |  | 42070.0418 |  |  | 42071.0418 |  |  | 42072.0418 |  |  | 42073.0418 |  |  | 42074.0418 |  |  | 42075.0418 |  |  | 42076.0418 |  |  | 42077.0418 |  |  | 42078.0418 |  |  | 42079.0418 |  |  | 42080.0418 |  |  | 42081.0418 | RIH 2,400 ft pre-drilled 7" liner |  | 42082.0418 | POOH from ± 16,236 ft to 9-5/8" shoe |  | 42083.0418 |  |  | 42084.0418 | C/O to 7" liner equipment |  | 42085.0418 | F/C well, POOH to surface |  | 42086.0418 |  |  | 42087.0418 |  |  | 42088.0418 |  |  | 42089.0418 |  |  | 42090.0418 |  |  | 42091.0418 | R/U Sline, install CRQ/DBSS, P/T, R/D Sline |  | 42092.0418 |  |  | 42093.0418 |  |  | 42094.0418 |  |  | 42095.0418 |  |  | 42096.0418
| 42054.0833 |  |  | 42055.0834 |  |  | 42056.0834 | N/U bell nipple |  | 42057.0834 |  |  | 42058.0834 |  |  | 42059.0834 | Pump sweeps, Circ hole clean |  | 42060.0834 |  |  | 42061.0834 | Heavy lift - N/U HP riser & BOP's |  | 42062.0834 |  |  | 42063.0834 |  |  | 42064.0834 |  |  | 42065.0834 |  |  | 42066.0834 |  |  | 42067.0834 |  |  | 42068.0834 |  |  | 42069.0834 | Make up CTT Test SOV to 3,500. POOH and L/O CTT. |  | 42070.0834 |  |  | 42071.0834 |  |  | 42072.0834 |  |  | 42073.0834 |  |  | 42074.0834 |  |  | 42075.0834 |  |  | 42076.0834 |  |  | 42077.0834 | Circ clean at 9-5/8" shoe, flow check |  | 42078.0834 |  |  | 42079.0834 |  |  | 42080.0834 |  |  | 42081.0834 |  |  | 42082.0834 |  |  | 42083.0834 | C/O to 5" DP equipment |  | 42084.0834 | RIH 7" liner # 4 p/u seal stem to PBR |  | 42085.0834 |  |  | 42086.0834 |  |  | 42087.0834 |  |  | 42088.0834 |  |  | 42089.0834 |  |  | 42090.0834 |  |  | 42091.0834 |  |  | 42092.0834 |  |  | 42093.0834 |  |  | 42094.0834 |  |  | 42095.0834 |  |  | 42096.0834
| 42054.125 |  |  | 42055.1251 |  |  | 42056.1251 | N/u flood line |  | 42057.1251 | Clean out conductor to 593 ft |  | 42058.1251 |  |  | 42059.1251 | B/R OOH to ± 1,800 ft |  | 42060.1251 |  |  | 42061.1251 |  |  | 42062.1251 |  |  | 42063.1251 |  |  | 42064.1251 |  |  | 42065.1251 |  |  | 42066.1251 |  |  | 42067.1251 |  |  | 42068.1251 | Displace & bump plug |  | 42069.1251 |  |  | 42070.1251 |  |  | 42071.1251 |  |  | 42072.1251 |  |  | 42073.1251 |  |  | 42074.1251 |  |  | 42075.1251 |  |  | 42076.1251 |  |  | 42077.1251 | Service TDS. Drops inspection F/C well, |  | 42078.1251 | Clean and clear rig floor and PJSM |  | 42079.1251 |  |  | 42080.1251 |  |  | 42081.1251 |  |  | 42082.1251 |  |  | 42083.1251 | M/U liner setting sleeve / PBR |  | 42084.1251 | RIH 1,500 ft pre-drilled 7" liner # 4 |  | 42085.1251 |  |  | 42086.1251 |  |  | 42087.1251 |  |  | 42088.1251 | P/U & M/U 1 jt x 3-1/2 tbg, 7" MFT pkr, x/o |  | 42089.1251 |  |  | 42090.1251 | Sting in and Space out |  | 42091.1251 |  |  | 42092.1251 |  |  | 42093.1251 |  |  | 42094.1251 |  |  | 42095.1251 |  |  | 42096.1251
| 42054.1667 |  |  | 42055.1668 | Heavy lift - Install XMT |  | 42056.1668 | M/U 17" Bit , Bit sub. RIH with clean out BHA |  | 42057.1668 | Drill 16" hole to ± 1,400 ft |  | 42058.1668 |  |  | 42059.1668 |  |  | 42060.1668 | P/U CSS hgr and RIH to ± 2,837 ft |  | 42061.1668 |  |  | 42062.1668 |  |  | 42063.1668 |  |  | 42064.1668 |  |  | 42065.1668 |  |  | 42066.1668 |  |  | 42067.1668 |  |  | 42068.1668 |  |  | 42069.1668 | Install short WB |  | 42070.1668 | Single in 59 stands with BHA |  | 42071.1668 |  |  | 42072.1668 |  |  | 42073.1668 |  |  | 42074.1668 |  |  | 42075.1668 |  |  | 42076.1668 |  |  | 42077.1668 |  |  | 42078.1668 | R/U 5" liner handling equipment and M/U bullnose |  | 42079.1668 | Dry Ream from +/- 17,300 ft to ± 23,800 ft, |  | 42080.1668 |  |  | 42081.1668 |  |  | 42082.1668 |  |  | 42083.1668 | RIH 7" liner # 3 on 5" DP to ± 16,100 ft |  | 42084.1668 |  |  | 42085.1668 |  |  | 42086.1668 |  |  | 42087.1668 |  |  | 42088.1668 |  |  | 42089.1668 |  |  | 42090.1668 |  |  | 42091.1668 |  |  | 42092.1668 |  |  | 42093.1668 |  |  | 42094.1668 |  |  | 42095.1668 |  |  | 42096.1668
| 42054.2083 |  |  | 42055.2084 |  |  | 42056.2084 |  |  | 42057.2084 |  |  | 42058.2084 |  |  | 42059.2084 |  |  | 42060.2084 | L/D upper bell nipple |  | 42061.2084 |  |  | 42062.2084 | Lay out 8" OD BHA |  | 42063.2084 |  |  | 42064.2084 |  |  | 42065.2084 |  |  | 42066.2084 | Circ 1.5 Btms Up |  | 42067.2084 |  |  | 42068.2084 | P/T casing 3,000 psi |  | 42069.2084 | Clear rig floor. |  | 42070.2084 |  |  | 42071.2084 |  |  | 42072.2084 |  |  | 42073.2084 |  |  | 42074.2084 |  |  | 42075.2084 |  |  | 42076.2084 |  |  | 42077.2084 | POOH laying down 31 stds, RIH 28 stds, POOH laying down 28 stds |  | 42078.2084 | RIH 5" 2,200 ft pre-drilled liner # 1 |  | 42079.2084 |  |  | 42080.2084 |  |  | 42081.2084 | C/O to 5" DP equipment |  | 42082.2084 |  |  | 42083.2084 |  |  | 42084.2084 |  |  | 42085.2084 |  |  | 42086.2084 |  |  | 42087.2084 |  |  | 42088.2084 | Change to 4 1/2 " RIH 1,400 ft 4-1/2" completion |  | 42089.2084 |  |  | 42090.2084 |  |  | 42091.2084 |  |  | 42092.2084 | Shear chem inj burst disc. Pump 30 bbls. |  | 42093.2084 |  |  | 42094.2084 |  |  | 42095.2084 |  |  | 42096.2084
| 42054.25 |  |  | 42055.2501 |  |  | 42056.2501 | Clean out conductor to 573 ft. POOH. |  | 42057.2501 |  |  | 42058.2501 |  |  | 42059.2501 |  |  | 42060.2501 |  |  | 42061.2501 |  |  | 42062.2501 |  |  | 42063.2501 |  |  | 42064.2501 |  |  | 42065.2501 |  |  | 42066.2501 | Flow check. Service TDS. |  | 42067.2501 |  |  | 42068.2501 | R/D cement lines and cmt head |  | 42069.2501 | P/U & rack 219 jts 5" DP |  | 42070.2501 |  |  | 42071.2501 |  |  | 42072.2501 |  |  | 42073.2501 |  |  | 42074.2501 |  |  | 42075.2501 |  |  | 42076.2501 |  |  | 42077.2501 |  |  | 42078.2501 |  |  | 42079.2501 |  |  | 42080.2501 |  |  | 42081.2501 | M/U liner setting sleeve / PBR |  | 42082.2501 |  |  | 42083.2501 |  |  | 42084.2501 | P/U Resman tracer and 200 ft BLANK liner, Mpas and Swell packers |  | 42085.2501 |  |  | 42086.2501 |  |  | 42087.2501 | Sting in and shear out Petrowell latch |  | 42088.2501 |  |  | 42089.2501 |  |  | 42090.2501 |  |  | 42091.2501 | L/D 7" landing string, clear rig floor |  | 42092.2501 | Prepare & skid to GD-21 |  | 42093.2501 |  |  | 42094.2501 |  |  | 42095.2501 |  |  | 42096.2501
| 42054.2917 |  |  | 42055.2918 |  |  | 42056.2918 |  |  | 42057.2918 |  |  | 42058.2918 |  |  | 42059.2918 | RIH to bottom |  | 42060.2918 | R/U cmt head & surface lines |  | 42061.2918 |  |  | 42062.2918 |  |  | 42063.2918 |  |  | 42064.2918 |  |  | 42065.2918 |  |  | 42066.2918 | B/R 5 stands for hole cleaning inside csg |  | 42067.2918 |  |  | 42068.2918 | Back out rng tool. POOH LD landing joints. |  | 42069.2918 |  |  | 42070.2918 |  |  | 42071.2918 |  |  | 42072.2918 |  |  | 42073.2918 |  |  | 42074.2918 |  |  | 42075.2918 |  |  | 42076.2918 |  |  | 42077.2918 |  |  | 42078.2918 |  |  | 42079.2918 |  |  | 42080.2918 |  |  | 42081.2918 | RIH 7" liner # 2 on 5" DP to ± 17,650 ft |  | 42082.2918 |  |  | 42083.2918 |  |  | 42084.2918 |  |  | 42085.2918 |  |  | 42086.2918 |  |  | 42087.2918 | Displace to Brine/SGA II |  | 42088.2918 |  |  | 42089.2918 |  |  | 42090.2918 | P/U tbg hanger, feed C/L through hgr |  | 42091.2918 | Heavy Lift - N/D Bell Nipple, BOP & Riser |  | 42092.2918 |  |  | 42093.2918 |  |  | 42094.2918 |  |  | 42095.2918 |  |  | 42096.2918
| 42054.3333 |  |  | 42055.3334 | P/T XMT void, hgr neck seal & body |  | 42056.3334 |  |  | 42057.3334 |  |  | 42058.3334 |  |  | 42059.3334 |  |  | 42060.3334 | Cement 1st Stage |  | 42061.3334 | Function test BOP's, install bell nipple |  | 42062.3334 |  |  | 42063.3334 |  |  | 42064.3334 |  |  | 42065.3334 |  |  | 42066.3334 |  |  | 42067.3334 |  |  | 42068.3334 |  |  | 42069.3334 |  |  | 42070.3334 |  |  | 42071.3334 |  |  | 42072.3334 |  |  | 42073.3334 |  |  | 42074.3334 |  |  | 42075.3334 |  |  | 42076.3334 |  |  | 42077.3334 |  |  | 42078.3334 |  |  | 42079.3334 |  |  | 42080.3334 |  |  | 42081.3334 |  |  | 42082.3334 |  |  | 42083.3334 |  |  | 42084.3334 | RIH 280 ft BLANK liner, 600 ft pre-drilled liner, P/U Resman tracer, 160 ft BLANK liner |  | 42085.3334 | L/O Liner Hanger running tool |  | 42086.3334 |  |  | 42087.3334 |  |  | 42088.3334 |  |  | 42089.3334 |  |  | 42090.3334 |  |  | 42091.3334 |  |  | 42092.3334 |  |  | 42093.3334 |  |  | 42094.3334 |  |  | 42095.3334 |  |  | 42096.3334
| 42054.375 |  |  | 42055.3751 |  |  | 42056.3751 |  |  | 42057.3751 |  |  | 42058.3751 |  |  | 42059.3751 | Pump sweeps, Spot KCl pill |  | 42060.3751 |  |  | 42061.3751 | Test well against ISR blind shear to 2,000psi |  | 42062.3751 | Rig Up SDC |  | 42063.3751 |  |  | 42064.3751 |  |  | 42065.3751 |  |  | 42066.3751 |  |  | 42067.3751 |  |  | 42068.3751 | Rig down 9-5/8" casing rng and fill up tools. |  | 42069.3751 |  |  | 42070.3751 |  |  | 42071.3751 |  |  | 42072.3751 |  |  | 42073.3751 |  |  | 42074.3751 |  |  | 42075.3751 | Circ 2 x B/U while staging OOH frm 23,800 to 23,500 ft |  | 42076.3751 |  |  | 42077.3751 |  |  | 42078.3751 | C/O to 7" equipt. Change PS21 to 7" |  | 42079.3751 |  |  | 42080.3751 |  |  | 42081.3751 |  |  | 42082.3751 |  |  | 42083.3751 |  |  | 42084.3751 |  |  | 42085.3751 | C/O to 4" DP handling equipment |  | 42086.3751 |  |  | 42087.3751 | POOH to TOL |  | 42088.3751 |  |  | 42089.3751 |  |  | 42090.3751 |  |  | 42091.3751 |  |  | 42092.3751 |  |  | 42093.3751 |  |  | 42094.3751 |  |  | 42095.3751 |  |  | 42096.3751
| 42054.4167 | #N/A |  | 42055.4168 |  |  | 42056.4168 | R/U and run 20" centroller gyro |  | 42057.4168 |  |  | 42058.4168 |  |  | 42059.4168 | POOH to surface |  | 42060.4168 | Displace cement, P/T 2,000 psi, check floats. |  | 42061.4168 | Install W/B |  | 42062.4168 | Run 13-3/8" centroller gyro |  | 42063.4168 |  |  | 42064.4168 |  |  | 42065.4168 |  |  | 42066.4168 | Slug pipe POOH to surface |  | 42067.4168 |  |  | 42068.4168 |  |  | 42069.4168 |  |  | 42070.4168 |  |  | 42071.4168 |  |  | 42072.4168 |  |  | 42073.4168 |  |  | 42074.4168 |  |  | 42075.4168 |  |  | 42076.4168 |  |  | 42077.4168 |  |  | 42078.4168 | P/U 5" x 7" x/o, |  | 42079.4168 |  |  | 42080.4168 |  |  | 42081.4168 |  |  | 42082.4168 | F/C well, POOH to surface |  | 42083.4168 |  |  | 42084.4168 | M/U liner hanger assy |  | 42085.4168 | M/U 6" bit on 7" scraper BHA |  | 42086.4168 |  |  | 42087.4168 | Displace to Completion Fluid |  | 42088.4168 | P/U & M/U sliding sleeve and Inj sub |  | 42089.4168 |  |  | 42090.4168 |  |  | 42091.4168 |  |  | 42092.4168 |  |  | 42093.4168 |  |  | 42094.4168 |  |  | 42095.4168 |  |  | 42096.4168
| 42054.4583 | Shear GLV, inflow test GLV |  | 42055.4584 | R/U Sline & PCE, ret. CRQ/DBSS, R/D S/L & PCE |  | 42056.4584 |  |  | 42057.4584 |  |  | 42058.4584 |  |  | 42059.4584 |  |  | 42060.4584 | Lift diverter and LP riser ± 3 ft |  | 42061.4584 | Lay out 16" BHA from derrick |  | 42062.4584 |  |  | 42063.4584 |  |  | 42064.4584 | Flow chk, change gear Hi, TD survey |  | 42065.4584 |  |  | 42066.4584 |  |  | 42067.4584 |  |  | 42068.4584 | M/U mill/flush tool. Flush riser, WH & BOP |  | 42069.4584 |  |  | 42070.4584 |  |  | 42071.4584 |  |  | 42072.4584 |  |  | 42073.4584 |  |  | 42074.4584 |  |  | 42075.4584 |  |  | 42076.4584 |  |  | 42077.4584 |  |  | 42078.4584 | RIH 7" x 2,400 ft pre-drilled liner # 1 |  | 42079.4584 |  |  | 42080.4584 |  |  | 42081.4584 |  |  | 42082.4584 |  |  | 42083.4584 |  |  | 42084.4584 | RIH 7" liner # 4 on 5" DP to ± 10,000 ft |  | 42085.4584 |  |  | 42086.4584 |  |  | 42087.4584 | POOH L/D 4" DP |  | 42088.4584 |  |  | 42089.4584 |  |  | 42090.4584 |  |  | 42091.4584 |  |  | 42092.4584 |  |  | 42093.4584 |  |  | 42094.4584 |  |  | 42095.4584 |  |  | 42096.4584
| 42054.5 | R/U Sline, install CRQ/DBSS, P/T, R/D Sline |  | 42055.5001 |  |  | 42056.5001 | Slip and cut D/L. Change out Martin decker. Replace saversub |  | 42057.5001 |  |  | 42058.5001 |  |  | 42059.5001 |  |  | 42060.5001 | Drop opening bomb, open DV collar |  | 42061.5001 | M/U 12-1/4" cleanout BHA and RIH to +/- 376 ft |  | 42062.5001 |  |  | 42063.5001 |  |  | 42064.5001 | B/R OOH Hawar 7,179 ft to 5,866 ft 40 mins/std |  | 42065.5001 | B/R OOH NU from 4,075 ft to 3638 ft 40 mins/std |  | 42066.5001 |  |  | 42067.5001 |  |  | 42068.5001 |  |  | 42069.5001 |  |  | 42070.5001 |  |  | 42071.5001 |  |  | 42072.5001 |  |  | 42073.5001 |  |  | 42074.5001 |  |  | 42075.5001 |  |  | 42076.5001 |  |  | 42077.5001 |  |  | 42078.5001 |  |  | 42079.5001 |  |  | 42080.5001 |  |  | 42081.5001 |  |  | 42082.5001 |  |  | 42083.5001 |  |  | 42084.5001 |  |  | 42085.5001 | Pick up 16 stds of 4" DP |  | 42086.5001 |  |  | 42087.5001 |  |  | 42088.5001 |  |  | 42089.5001 |  |  | 42090.5001 |  |  | 42091.5001 | Remove comms collar, terminate C/L's, install hgr neck seal |  | 42092.5001 |  |  | 42093.5001 |  |  | 42094.5001 |  |  | 42095.5001 |  |  | 42096.5001
| 42054.5417 |  |  | 42055.5418 |  |  | 42056.5418 |  |  | 42057.5418 |  |  | 42058.5418 |  |  | 42059.5418 |  |  | 42060.5418 | Cement 2nd Stage. Displace closing plug to stage collar. |  | 42061.5418 |  |  | 42062.5418 | Rig down |  | 42063.5418 |  |  | 42064.5418 |  |  | 42065.5418 |  |  | 42066.5418 |  |  | 42067.5418 |  |  | 42068.5418 | Install & P-test MS-T seal |  | 42069.5418 |  |  | 42070.5418 |  |  | 42071.5418 |  |  | 42072.5418 |  |  | 42073.5418 |  |  | 42074.5418 |  |  | 42075.5418 | B/R f/ 23,500 ft to shoe at 8,742 ft taking 2 caliper stations |  | 42076.5418 |  |  | 42077.5418 |  |  | 42078.5418 |  |  | 42079.5418 |  |  | 42080.5418 | Slip & Cut Drilling Line |  | 42081.5418 |  |  | 42082.5418 |  |  | 42083.5418 | Drop setting ball & release liner |  | 42084.5418 |  |  | 42085.5418 |  |  | 42086.5418 |  |  | 42087.5418 |  |  | 42088.5418 | M/U 9-5/8" MFR pkr , terminate C/L's |  | 42089.5418 |  |  | 42090.5418 |  |  | 42091.5418 |  |  | 42092.5418 |  |  | 42093.5418 |  |  | 42094.5418 |  |  | 42095.5418 |  |  | 42096.5418
| 42054.5833 |  |  | 42055.5834 |  |  | 42056.5834 |  |  | 42057.5834 |  |  | 42058.5834 |  |  | 42059.5834 |  |  | 42060.5834 |  |  | 42061.5834 | RIH and tag Closing plug at 571 ft |  | 42062.5834 | P/U & M/U 12-1/4" PDC Xceed BHA |  | 42063.5834 |  |  | 42064.5834 |  |  | 42065.5834 |  |  | 42066.5834 | L/D jars and accelerator |  | 42067.5834 |  |  | 42068.5834 |  |  | 42069.5834 |  |  | 42070.5834 |  |  | 42071.5834 |  |  | 42072.5834 |  |  | 42073.5834 |  |  | 42074.5834 |  |  | 42075.5834 |  |  | 42076.5834 |  |  | 42077.5834 |  |  | 42078.5834 |  |  | 42079.5834 |  |  | 42080.5834 | F/C well, POOH to surface |  | 42081.5834 |  |  | 42082.5834 |  |  | 42083.5834 |  |  | 42084.5834 |  |  | 42085.5834 |  |  | 42086.5834 |  |  | 42087.5834 |  |  | 42088.5834 |  |  | 42089.5834 |  |  | 42090.5834 | Install comms collar & seal assy |  | 42091.5834 |  |  | 42092.5834 |  |  | 42093.5834 |  |  | 42094.5834 |  |  | 42095.5834 |  |  | 42096.5834
| 42054.625 |  |  | 42055.6251 | Shear chem inj sub. Pump 30 bbls via LVO. |  | 42056.6251 |  |  | 42057.6251 |  |  | 42058.6251 |  |  | 42059.6251 | R/B 16" BHA |  | 42060.6251 | R/D cmt head |  | 42061.6251 | Drill out DV collar/ plugs |  | 42062.6251 |  |  | 42063.6251 |  |  | 42064.6251 |  |  | 42065.6251 |  |  | 42066.6251 | L/D DC's, MWD, and RSS |  | 42067.6251 |  |  | 42068.6251 | POOH seal rng tool. Inspect. OK. |  | 42069.6251 |  |  | 42070.6251 |  |  | 42071.6251 |  |  | 42072.6251 |  |  | 42073.6251 | Drill 8-1/2" hole frm 18,923 ft to 19,768 ft |  | 42074.6251 | Drill 8-1/2" hole frm 20,670 ft to 23,800 ft TD |  | 42075.6251 |  |  | 42076.6251 |  |  | 42077.6251 |  |  | 42078.6251 |  |  | 42079.6251 |  |  | 42080.6251 |  |  | 42081.6251 |  |  | 42082.6251 | L/O Liner # 2 running tool |  | 42083.6251 | B/R from 11,484 ft to 9-5/8" shoe at 8,742 ft |  | 42084.6251 |  |  | 42085.6251 |  |  | 42086.6251 |  |  | 42087.6251 |  |  | 42088.6251 |  |  | 42089.6251 | P/U & M/U 1 jt 4-1/2" tbg, SPM |  | 42090.6251 |  |  | 42091.6251 |  |  | 42092.6251 |  |  | 42093.6251 |  |  | 42094.6251 |  |  | 42095.6251 |  |  | 42096.6251
| 42054.6667 | L/D 7" landing string, clear RF |  | 42055.6668 |  |  | 42056.6668 | P/U & M/U 16" RSS BHA |  | 42057.6668 |  |  | 42058.6668 |  |  | 42059.6668 |  |  | 42060.6668 | Cut 13-3/8" csg @ 73" above TOS |  | 42061.6668 |  |  | 42062.6668 |  |  | 42063.6668 |  |  | 42064.6668 |  |  | 42065.6668 |  |  | 42066.6668 |  |  | 42067.6668 |  |  | 42068.6668 |  |  | 42069.6668 |  |  | 42070.6668 |  |  | 42071.6668 |  |  | 42072.6668 |  |  | 42073.6668 |  |  | 42074.6668 |  |  | 42075.6668 |  |  | 42076.6668 |  |  | 42077.6668 |  |  | 42078.6668 | P/U Resman tracer joint |  | 42079.6668 |  |  | 42080.6668 |  |  | 42081.6668 |  |  | 42082.6668 | C/O to 7" liner equipment |  | 42083.6668 |  |  | 42084.6668 |  |  | 42085.6668 | P/U 9-5/8" scraper BHA |  | 42086.6668 |  |  | 42087.6668 |  |  | 42088.6668 |  |  | 42089.6668 | RIH 750 ft 4-1/2" completion |  | 42090.6668 |  |  | 42091.6668 |  |  | 42092.6668 |  |  | 42093.6668 |  |  | 42094.6668 |  |  | 42095.6668 |  |  | 42096.6668
| 42054.7083 | Heavy Lift - N/D Bell Nipple, BOP & Riser |  | 42055.7084 | Depressurize X-mas tree and prepare for skidding operations |  | 42056.7084 |  |  | 42057.7084 |  |  | 42058.7084 |  |  | 42059.7084 |  |  | 42060.7084 |  |  | 42061.7084 | RIH 12-1/4" BHA to +/- 2,787 ft |  | 42062.7084 |  |  | 42063.7084 |  |  | 42064.7084 |  |  | 42065.7084 |  |  | 42066.7084 |  |  | 42067.7084 |  |  | 42068.7084 | POOH and rack back HWDP. |  | 42069.7084 |  |  | 42070.7084 |  |  | 42071.7084 |  |  | 42072.7084 |  |  | 42073.7084 |  |  | 42074.7084 |  |  | 42075.7084 |  |  | 42076.7084 |  |  | 42077.7084 | POOH 5" DP to BHA |  | 42078.7084 | M/U liner setting sleeve / PBR |  | 42079.7084 |  |  | 42080.7084 |  |  | 42081.7084 |  |  | 42082.7084 | PJSM, RIH 7" liner # 3 p/u seal stem to PBR |  | 42083.7084 |  |  | 42084.7084 |  |  | 42085.7084 |  |  | 42086.7084 | Install X/O and Petrowell Latch assy |  | 42087.7084 |  |  | 42088.7084 |  |  | 42089.7084 |  |  | 42090.7084 |  |  | 42091.7084 | Heavy lift - Install XMT |  | 42092.7084 |  |  | 42093.7084 |  |  | 42094.7084 |  |  | 42095.7084 |  |  | 42096.7084
| 42054.75 |  |  | 42055.7501 | Skid to WELL abc, Secure rig |  | 42056.7501 |  |  | 42057.7501 | Spot pill, POOH |  | 42058.7501 |  |  | 42059.7501 | R/U csg equipment |  | 42060.7501 | L/D 13-3/8" csg stump, R/D handling eqpt |  | 42061.7501 |  |  | 42062.7501 | RIH on 5" DP to ± 1,600 ft |  | 42063.7501 |  |  | 42064.7501 |  |  | 42065.7501 |  |  | 42066.7501 | Pull Wear Bushing |  | 42067.7501 |  |  | 42068.7501 | Change 9-5/8" rams to blind rams |  | 42069.7501 |  |  | 42070.7501 | Service TDS. Set Torque sync. Calibrate depth sensors. |  | 42071.7501 |  |  | 42072.7501 |  |  | 42073.7501 | Drill 8-1/2" hole frm 19,768 ft to 20,670 ft |  | 42074.7501 |  |  | 42075.7501 |  |  | 42076.7501 |  |  | 42077.7501 |  |  | 42078.7501 | RIH 5 x 7" liner # 1 on 5" DP to ± 17,300 ft |  | 42079.7501 | Drop setting ball & release liner |  | 42080.7501 |  |  | 42081.7501 | Dry Ream from ± 17,650 ft to ± 19,168 ft |  | 42082.7501 | RIH 4,725 ft pre-drilled 7" liner #3 |  | 42083.7501 |  |  | 42084.7501 | P/U 5 stds HWDP and 21 singles of HWDP |  | 42085.7501 | Scrape pkr setting intervals 8,006 ft and 9,511 ft |  | 42086.7501 | RIH lower completion on +- 12 stds 4" DP |  | 42087.7501 |  |  | 42088.7501 |  |  | 42089.7501 |  |  | 42090.7501 | Land hanger, P/T annular seal, O/P test |  | 42091.7501 |  |  | 42092.7501 |  |  | 42093.7501 |  |  | 42094.7501 |  |  | 42095.7501 |  |  | 42096.7501
| 42054.7917 |  |  | 42055.7918 |  |  | 42056.7918 |  |  | 42057.7918 |  |  | 42058.7918 |  |  | 42059.7918 |  |  | 42060.7918 |  |  | 42061.7918 | Drill out plugs, baffle, shoe track cement and shoe |  | 42062.7918 | Shallow test tools |  | 42063.7918 |  |  | 42064.7918 |  |  | 42065.7918 |  |  | 42066.7918 | Jet WH and BOP. |  | 42067.7918 |  |  | 42068.7918 |  |  | 42069.7918 |  |  | 42070.7918 | RIH, drill out cmt, displace to 9.5 ppg mud. |  | 42071.7918 |  |  | 42072.7918 |  |  | 42073.7918 |  |  | 42074.7918 |  |  | 42075.7918 |  |  | 42076.7918 |  |  | 42077.7918 |  |  | 42078.7918 |  |  | 42079.7918 | B/R OOH 3 stds |  | 42080.7918 |  |  | 42081.7918 |  |  | 42082.7918 |  |  | 42083.7918 | F/C well, POOH to surface |  | 42084.7918 |  |  | 42085.7918 | R/U 3-1/2" handling equipment |  | 42086.7918 |  |  | 42087.7918 |  |  | 42088.7918 |  |  | 42089.7918 | P/U & M/U TRMAXX SSSV |  | 42090.7918 |  |  | 42091.7918 |  |  | 42092.7918 |  |  | 42093.7918 |  |  | 42094.7918 |  |  | 42095.7918 |  |  | 42096.7918
| 42054.8333 |  |  | 42055.8334 | Perform DROPS survey & install roller |  | 42056.8334 |  |  | 42057.8334 | L/D Motor |  | 42058.8334 |  |  | 42059.8334 | RIH 13-3/8" casing to ± 2,250 ft |  | 42060.8334 | Heavy lift - N/D diverter & LP riser |  | 42061.8334 |  |  | 42062.8334 | RIH to 2,847 ft . Downlink Xceed |  | 42063.8334 |  |  | 42064.8334 |  |  | 42065.8334 | B/R OOH from 3,638 ft to 3,170 ft 20 mins/std |  | 42066.8334 |  |  | 42067.8334 | R/U cmt head & HP lines |  | 42068.8334 | M/U test plug, full BOP test. |  | 42069.8334 |  |  | 42070.8334 |  |  | 42071.8334 |  |  | 42072.8334 |  |  | 42073.8334 |  |  | 42074.8334 |  |  | 42075.8334 |  |  | 42076.8334 |  |  | 42077.8334 |  |  | 42078.8334 |  |  | 42079.8334 | F/C well, POOH 5 stds wet |  | 42080.8334 | C/O to 7" liner equipment, PJSM |  | 42081.8334 |  |  | 42082.8334 |  |  | 42083.8334 |  |  | 42084.8334 |  |  | 42085.8334 |  |  | 42086.8334 | Change to 5" DP and RIH to setting depth 18,663 ft (90 stds) |  | 42087.8334 | Pull WB and jet wehead with Multi-task filter |  | 42088.8334 |  |  | 42089.8334 | RIH 1,890 ft 4-1/2" completion |  | 42090.8334 |  |  | 42091.8334 |  |  | 42092.8334 |  |  | 42093.8334 |  |  | 42094.8334 |  |  | 42095.8334 |  |  | 42096.8334
| 42054.875 |  |  | 42055.8751 |  |  | 42056.8751 |  |  | 42057.8751 | P/U & M/U PD1100 BHA |  | 42058.8751 |  |  | 42059.8751 |  |  | 42060.8751 |  |  | 42061.8751 | Drill out 10 ft of new formation to 2,847 ft . C&C mud. |  | 42062.8751 | Drill 12-1/4" hole from 2,847 ft to 7,179 ft |  | 42063.8751 |  |  | 42064.8751 |  |  | 42065.8751 |  |  | 42066.8751 | R/U csg equipment |  | 42067.8751 | Rig pump lo rheology mud |  | 42068.8751 |  |  | 42069.8751 |  |  | 42070.8751 |  |  | 42071.8751 |  |  | 42072.8751 |  |  | 42073.8751 |  |  | 42074.8751 |  |  | 42075.8751 |  |  | 42076.8751 |  |  | 42077.8751 |  |  | 42078.8751 |  |  | 42079.8751 | POOH to 9-5/8" shoe |  | 42080.8751 |  |  | 42081.8751 |  |  | 42082.8751 |  |  | 42083.8751 |  |  | 42084.8751 | RIH 7" liner # 4 on 5" DP to ± 11,484 ft |  | 42085.8751 | P/U & M/U and RIH 9,000 ft 3 1/2" tbg. Fill tbg every 10 joints |  | 42086.8751 |  |  | 42087.8751 |  |  | 42088.8751 |  |  | 42089.8751 |  |  | 42090.8751 |  |  | 42091.8751 | P/T XMT void, hgr neck seal & body |  | 42092.8751 |  |  | 42093.8751 |  |  | 42094.8751 |  |  | 42095.8751 |  |  | 42096.8751
| 42054.9167 | Remove comms, term. C/L's, install hgr neck seal |  | 42055.9168 | Heavy Lift - Install LP Riser |  | 42056.9168 |  |  | 42057.9168 |  |  | 42058.9168 |  |  | 42059.9168 |  |  | 42060.9168 | Heavy lift - N/U & P/T WH |  | 42061.9168 |  |  | 42062.9168 |  |  | 42063.9168 |  |  | 42064.9168 |  |  | 42065.9168 |  |  | 42066.9168 |  |  | 42067.9168 |  |  | 42068.9168 |  |  | 42069.9168 |  |  | 42070.9168 |  |  | 42071.9168 |  |  | 42072.9168 |  |  | 42073.9168 |  |  | 42074.9168 |  |  | 42075.9168 |  |  | 42076.9168 |  |  | 42077.9168 | Reset WB recovered on BHA |  | 42078.9168 |  |  | 42079.9168 |  |  | 42080.9168 | RIH 200 ft of 7" BLANK liner #2 |  | 42081.9168 | Sting in, drop setting ball & release liner |  | 42082.9168 |  |  | 42083.9168 |  |  | 42084.9168 | Sting in, Drop ball, Set liner top packer and release RT |  | 42085.9168 |  |  | 42086.9168 |  |  | 42087.9168 | PJSM R/U to run 4 1/2" completion assy. |  | 42088.9168 | RIH 5,250 ft 4-1/2" completion |  | 42089.9168 |  |  | 42090.9168 | Set 9-5/8" MFR and MFT pkrs, P/T tbg |  | 42091.9168 |  |  | 42092.9168 |  |  | 42093.9168 |  |  | 42094.9168 |  |  | 42095.9168 |  |  | 42096.9168
| 42054.9583 |  |  | 42055.9584 | N/U diverter |  | 42056.9584 | Shallow pulse test MWD |  | 42057.9584 | Wiper trip. RIH with PD1100 to 1,400 ft |  | 42058.9584 |  |  | 42059.9584 |  |  | 42060.9584 |  |  | 42061.9584 |  |  | 42062.9584 |  |  | 42063.9584 |  |  | 42064.9584 |  |  | 42065.9584 |  |  | 42066.9584 |  |  | 42067.9584 |  |  | 42068.9584 |  |  | 42069.9584 |  |  | 42070.9584 |  |  | 42071.9584 | Drill 8-1/2" hole frm 11,600 ft to 16,190 ft |  | 42072.9584 | Drill 8-1/2" hole frm 16,190 ft to 18,923 ft |  | 42073.9584 |  |  | 42074.9584 |  |  | 42075.9584 |  |  | 42076.9584 |  |  | 42077.9584 | L/D 8-1/2" Xceed BHA |  | 42078.9584 |  |  | 42079.9584 |  |  | 42080.9584 | PJSM, P/U MPas & Swell pkr, |  | 42081.9584 | B/R 3 stds, F/C well |  | 42082.9584 |  |  | 42083.9584 |  |  | 42084.9584 |  |  | 42085.9584 |  |  | 42086.9584 |  |  | 42087.9584 |  |  | 42088.9584 |  |  | 42089.9584 |  |  | 42090.9584 | Inflow test SSSV, P/T C Section |  | 42091.9584 |  |  | 42092.9584 |  |  | 42093.9584 |  |  | 42094.9584 |  |  | 42095.9584 |  |  | 42096.9584
| EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG |  |  | EQUIPMENT FROM RIG
[49 empty] | KCL Brine - 650 bbl | [5 empty] | 9-5/8" Casing and acc |  |  | Casing handling tools | [50 empty] | Remaining 7" Liner
[49 empty] | Empty Food container Dry and Refer | [11 empty] | 18ft Bails ( IFT AJA) | [23 empty] | Cac03 - 30 Mt | [5 empty] | Cac03 - 30 Mt | [17 empty] | W/ford Running tools
[49 empty] | Empty cementing chemical containers |  |  | SLB tools |  |  | 6-1/2" Jar and acc | [5 empty] | 16" Drill Bit ( IFT from AJA) |  |  | Used 8-1/2" Drill Bits - 2 Ea | [20 empty] | 8-1/2" Drilling tools SLB |  |  | 8-1/2" Drilling tools SLB ( IFT AJA) |  |  | 4" Drill pipe | [17 empty] | Almasood handling tools
[52 empty] | Spiro Torq | [11 empty] | Microseal centraliser | [20 empty] | 5" Drill pipes - 175 Joints | [5 empty] | SLB Tools
[55 empty] | SLB tools ( IFT RCA) | [8 empty] | Expendolisers and stop rings | [23 empty] | IF - RTTS to LHA
[64 empty] | Couplings - 9-5/8" | [23 empty] | Remaining 5" Liner
| EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG |  |  | EQUIPMENT TO RIG | [5 empty] | EQUIPMENT TO RIG
| Drill H2O |  |  | XX-MR-01 Casing & Accessories |  |  | Drillwater 200 MT (Kehoe Tide)
| Bentonite 30MT |  |  | MR-01-DQ WH | [8 empty] | 12 1/4"Mud Chem(CMR-05) |  |  | 12 1/4"Mud Chem(CMR-06) |  |  | 12 1/4"Mud Chem(CMR-07) |  |  | 9-5/8" Casing (MR # 4)
|  |  |  | MR-01 - Hall cement head |  |  | BAD WEATHER |  |  | BAD WEATHER | [8 empty] | 12-1/4" RSS BHA (MR 05) |  |  | 60 MT Elasticem cement (CMR 09) |  |  | 9-5/8" cementing chemicals (CMR 08) | [5 empty] | 170 JOINTS 5" DP (MR 06)
[13 empty] | BAD WEATHER | [11 empty] | Elasticem cement (CMR 09)
| TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM | TO | PERSONNEL | FROM
| 15 | Shelf | 14 |  | HLB Evo trieve | 3 | 2 | Baker e-Line |  | 1 | Mud engr | 1 | 3 | AL Masaood |  | 1 | New Medic(Shelf) |  | 1 | Data Engr.(Weatherford) | 1 | 11 | Shelf C/C | 12 |  |  |  | 1 | Data Engr.(Wfd) | 1 |  |  |  | 6 | Al-Masood | [7 empty] | 19 | SHELF C/C | 19
| 2 | SLB D&M |  |  |  |  | 1 | Campboss(Teyseer) | 1 |  | Baker e-Line | 2 |  | (above booking confirmed) |  | 1 | James Granger |  |  | (above booking confirmed) |  | 1 | WSG(MITAS) | [5 empty] | SDC | 2 |  |  |  |  | (above booking confirmed) | [7 empty] | 1 | Jim DSV | [85 empty] | 1 | Allan DSV Leo | 1
| 2 | Gyrodata |  |  | Al Masaood | 1 | 1 | Cementer(Hall) |  |  | WSS | 1 |  |  |  | 1 | Ian |  |  |  |  | 1 | Ian(RSTC) | [5 empty] | (above booking confirmed) | [101 empty] | Chris Lemsom | 1
|  | Aggreko(Shelf) | 1 |  | Drill Qup | 1 |  | rstc(IAN) | 1 | 1 | Halliburton (CMT helper) |  |  | NOV Centrifuge engineer | 1 |  | (above booking confirmed) | [5 empty] | James Granger | 1
| 5 | Bernd DSV | 1 | 1 | NOV ( RA change out) |  |  | SLB S/line | 2 |  | Cementer | 1 | [10 empty] | (above booking confirmed)
|  | (above booking confirmed) |  | 4 | Painters |  |  | HLB Evo trieve | 2 |  | Teyseer(cook) | 1 |  |  |  |  | Gyrodata | 2 | [13 empty] | (No Seats Available)
[5 empty] | (above booking confirmed) |  |  | WSS | 1 |  | (above booking confirmed) | [7 empty] | 1 | NOV centrifuge engineer |  | 2 | MOQ Geologist
[8 empty] | Drill Quip | 3 | [9 empty] | 1 | WSE (Kevin Pearce) |  |  | Al-Masood | 5
[8 empty] | (above booking confirmed) | [13 empty] | 2 | Weatherford sample catchers
[23 empty] | DQ Engineer | 2
| 24 |  | 16 | 5 |  | 5 | 4 |  | 10 | 2 |  | 6 | 3 |  | 1 | 3 |  | 2 | 3 |  | 1 | 17 |  | 20 | 0 |  | 0 | 1 |  | 3 | 0 |  | 0 | 6 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20 |  | 19 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
98 | POB |  | 106 | POB |  | 106 | POB |  | 100 | POB |  | 96 | POB |  | 98 | POB |  | 99 | POB |  | 101 | POB |  | 98 | POB |  | 98 | POB |  | 96 | POB |  | 96 | POB |  | 102 | POB |  | 102 | POB |  | 102 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103 | POB |  | 103
| VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS |  |  | VESSELS
| 2015-02-19 |  |  | 2015-02-20 |  |  | 2015-02-21 |  |  | 2015-02-22 |  |  | 2015-02-23 |  |  | 2015-02-24 |  |  | 2015-02-25 |  |  | 2015-02-26 |  |  | 2015-02-27 |  |  | 2015-02-28 |  |  | 2015-03-01 |  |  | 2015-03-02 |  |  | 2015-03-03 |  |  | 2015-03-04 |  |  | 2015-03-05 |  |  | 2015-03-06 |  |  | 2015-03-07 |  |  | 2015-03-08 |  |  | 2015-03-09 |  |  | 2015-03-10 |  |  | 2015-03-11 |  |  | 2015-03-12 |  |  | 2015-03-13 |  |  | 2015-03-14 |  |  | 2015-03-15 |  |  | 2015-03-16 |  |  | 2015-03-17 |  |  | 2015-03-18 |  |  | 2015-03-19 |  |  | 2015-03-20 |  |  | 2015-03-21 |  |  | 2015-03-22 |  |  | 2015-03-23 |  |  | 2015-03-24 |  |  | 2015-03-25 |  |  | 2015-03-26 |  |  | 2015-03-27 |  |  | 2015-03-28 |  |  | 2015-03-29 |  |  | 2015-03-30 |  |  | 2015-03-31 |  |  | 2015-04-01 |  |  | 2015-04-02
............................................................................................................................
Formulas:
EQUIPMENT FROM RIG = [EQUIPMENT FROM RIG]+1
abc

## Time Breakdown
OPERATIONS FORECAST
Rig Name | My drilling rig name | Start Date |  | 2015-02-19
Project Name | AB-123 | Start Time |  | 9:30
POB Capacity | 106 | Next BOP Test
Start | Operation Description / Activity | EST | ACT | End | Total | Remarks
Time |  | HRS | HRS | Time | Time
2015-02-19 09:30 |  | 0 |  | 2015-02-19 09:30
2015-02-19 09:30 | Inflow test SSSV, P/T C Section | 1.5 | 1.5 | 2015-02-19 11:00
2015-02-19 11:00 | Shear GLV, inflow test GLV | 1 | 1 | 2015-02-19 12:00
2015-02-19 12:00 | R/U Sline, install CRQ/DBSS, P/T, R/D Sline | 4.5 | 3.5 | 2015-02-19 15:30
2015-02-19 15:30 | L/D 7" landing string, clear RF | 1 | 1 | 2015-02-19 16:30
2015-02-19 16:30 | Heavy Lift - N/D Bell Nipple, BOP & Riser | 5 | 5.5 | 2015-02-19 22:00
2015-02-19 22:00 | Remove comms, term. C/L's, install hgr neck seal | 9 | 6 | 2015-02-20 04:00
2015-02-20 04:00 | Heavy lift - Install XMT | 4 | 4 | 2015-02-20 08:00
2015-02-20 08:00 | P/T XMT void, hgr neck seal & body | 3 | 3 | 2015-02-20 11:00
2015-02-20 11:00 | R/U Sline & PCE, ret. CRQ/DBSS, R/D S/L & PCE | 3.5 | 3.5 | 2015-02-20 14:30
2015-02-20 14:30 | Shear chem inj sub. Pump 30 bbls via LVO. | 2 | 2 | 2015-02-20 16:30
2015-02-20 16:30 | Depressurize X-mas tree and prepare for skidding operations | 1.5 | 1.5 | 2015-02-20 18:00
2015-02-20 18:00 | Skid to WELL abc, Secure rig | 1 | 1.5 | 2015-02-20 19:30
2015-02-20 19:30 | Perform DROPS survey & install roller | 1.5 | 2 | 2015-02-20 21:30
2015-02-20 21:30 | Heavy Lift - Install LP Riser | 1.5 | 1 | 2015-02-20 22:30
2015-02-20 22:30 | Install half hatch covers | 0.5 | 0.5 | 2015-02-20 23:00
2015-02-20 23:00 | N/U diverter | 4 | 3 | 2015-02-21 02:00
2015-02-21 02:00 | N/U bell nipple | 1.5 | 1 | 2015-02-21 03:00
2015-02-21 03:00 | N/u flood line | 1 | 0.5 | 2015-02-21 03:30
2015-02-21 03:30 | Function test divert, activate LP packer, hydrotest rig up | 1 | 0.5 | 2015-02-21 04:00
2015-02-21 04:00 | M/U 17" Bit , Bit sub. RIH with clean out BHA | 2 | 1.5 | 2015-02-21 05:30
2015-02-21 05:30 | Test diverter 50 psi / 5 mins | 0.5 | 0.5 | 2015-02-21 06:00
2015-02-21 06:00 | Clean out conductor to 573 ft. POOH. | 5.5 | 4 | 2015-02-21 10:00
2015-02-21 10:00 | R/U and run 20" centroller gyro | 3 | 2 | 2015-02-21 12:00
2015-02-21 12:00 | Drill 16" HOLE |  |  | 2015-02-21 12:00
2015-02-21 12:00 | Install mouse hole | 0 | 0 | 2015-02-21 12:00
2015-02-21 12:00 | Slip and cut D/L. Change out Martin decker. Replace saversub | 6 | 4 | 2015-02-21 16:00 |  | Planned rig maintenance
2015-02-21 16:00 | P/U & M/U 16" RSS BHA | 8 | 7 | 2015-02-21 23:00
2015-02-21 23:00 | Shallow pulse test MWD | 0.5 | 0.5 | 2015-02-21 23:30
2015-02-21 23:30 | Callibrate ML & MWD depth sensors. | 0.5 | 0.5 | 2015-02-22
2015-02-22 | RIH 5" HWDP to ± 575 ft | 0.5 | 0.5 | 2015-02-22 00:30
2015-02-22 00:30 | Gyro data take check shot survey. SDC take one gyro single shot survey | 1 | 2.5 | 2015-02-22 03:00
2015-02-22 03:00 | Clean out conductor to 593 ft | 1 | 1 | 2015-02-22 04:00
2015-02-22 04:00 | Drill 16" hole to ± 1,400 ft | 14 |  | 2015-02-22 18:00 |  | XX: Avg ROP 63 ft/ hr (PD1100 BHA)
2015-02-22 18:00 | Spot pill, POOH | 2 |  | 2015-02-22 20:00 |  | If BHA is changed from Motor to RSS
2015-02-22 20:00 | L/D Motor | 0.5 |  | 2015-02-22 20:30
2015-02-22 20:30 | L/D GMWD | 0.5 |  | 2015-02-22 21:00
2015-02-22 21:00 | P/U & M/U PD1100 BHA | 1.5 |  | 2015-02-22 22:30
2015-02-22 22:30 | Test PD1100 BHA | 0.5 |  | 2015-02-22 23:00
2015-02-22 23:00 | Wiper trip. RIH with PD1100 to 1,400 ft | 2 |  | 2015-02-23 01:00
2015-02-23 01:00 | Drill 16" hole to ± 2,837 ft | 25 |  | 2015-02-24 02:00 |  | GD-18: Avg ROP 58 ft/ hr (PD1100 BHA)
2015-02-24 02:00 | Pump sweeps, Circ hole clean | 1 |  | 2015-02-24 03:00
2015-02-24 03:00 | B/R OOH to ± 1,800 ft | 4 |  | 2015-02-24 07:00
2015-02-24 07:00 | RIH to bottom | 1.5 |  | 2015-02-24 08:30
2015-02-24 08:30 | Pump sweeps, Spot KCl pill | 1 |  | 2015-02-24 09:30
2015-02-24 09:30 | POOH to surface | 5 |  | 2015-02-24 14:30
2015-02-24 14:30 | R/B 16" BHA | 3 |  | 2015-02-24 17:30
2015-02-24 17:30 | Run 13-3/8" Casing |  |  | 2015-02-24 17:30
2015-02-24 17:30 | R/U csg equipment | 2 |  | 2015-02-24 19:30
2015-02-24 19:30 | RIH 13-3/8" casing to ± 2,250 ft | 8 |  | 2015-02-25 03:30
2015-02-25 03:30 | P/U CSS hgr and RIH to ± 2,837 ft | 1 |  | 2015-02-25 04:30 |  | CSS @ ± 578 ft
2015-02-25 04:30 | Land CSS hanger. Confirm seals holding | 0.5 |  | 2015-02-25 05:00
2015-02-25 05:00 | L/D upper bell nipple | 1.5 |  | 2015-02-25 06:30
2015-02-25 06:30 | R/U cmt head & surface lines | 1 |  | 2015-02-25 07:30
2015-02-25 07:30 | Flush and P/T surface lines | 0.5 |  | 2015-02-25 08:00
2015-02-25 08:00 | Cement 1st Stage | 1.5 |  | 2015-02-25 09:30
2015-02-25 09:30 | Displace cement, P/T 2,000 psi, check floats. | 1.5 |  | 2015-02-25 11:00
2015-02-25 11:00 | Lift diverter and LP riser ± 3 ft | 1 |  | 2015-02-25 12:00
2015-02-25 12:00 | Drop opening bomb, open DV collar | 1 |  | 2015-02-25 13:00
2015-02-25 13:00 | Cement 2nd Stage. Displace closing plug to stage collar. | 1.5 |  | 2015-02-25 14:30
2015-02-25 14:30 | P/T Csg to 2,000 psi. Check DV ports sealed. | 0.5 |  | 2015-02-25 15:00
2015-02-25 15:00 | R/D cmt head | 0.5 |  | 2015-02-25 15:30
2015-02-25 15:30 | Cut 13-3/8" csg @ 73" above TOS | 2 |  | 2015-02-25 17:30
2015-02-25 17:30 | L/D 13-3/8" csg stump, R/D handling eqpt | 2 |  | 2015-02-25 19:30
2015-02-25 19:30 | Heavy lift - N/D diverter & LP riser | 2 |  | 2015-02-25 21:30
2015-02-25 21:30 | Heavy lift - N/U & P/T WH | 4 |  | 2015-02-26 01:30
2015-02-26 01:30 | Heavy lift - N/U HP riser & BOP's | 6 |  | 2015-02-26 07:30
2015-02-26 07:30 | Function test BOP's, install bell nipple | 1.5 |  | 2015-02-26 09:00
2015-02-26 09:00 | Test well against ISR blind shear to 2,000psi | 0.5 |  | 2015-02-26 09:30
2015-02-26 09:30 | Install W/B | 1 |  | 2015-02-26 10:30
2015-02-26 10:30 | Lay out 16" BHA from derrick | 1.5 |  | 2015-02-26 12:00
2015-02-26 12:00 | Drill 12-1/4" Hole |  |  | 2015-02-26 12:00
2015-02-26 12:00 | M/U 12-1/4" cleanout BHA and RIH to +/- 376 ft | 2 |  | 2015-02-26 14:00
2015-02-26 14:00 | M/u 9-5/8" csg test mandrel. Space out to 9-5/8" csg ram. | 0 |  | 2015-02-26 14:00
2015-02-26 14:00 | Attempt test casing | 0 |  | 2015-02-26 14:00
2015-02-26 14:00 | RIH and tag Closing plug at 571 ft | 0.5 |  | 2015-02-26 14:30
2015-02-26 14:30 | Drill out DV collar/ plugs | 2 |  | 2015-02-26 16:30
2015-02-26 16:30 | Pressure test 13-3/8" casing to 2,000 psi/ 10 mins | 0.5 |  | 2015-02-26 17:00
2015-02-26 17:00 | Choke drill | 0 |  | 2015-02-26 17:00
2015-02-26 17:00 | RIH 12-1/4" BHA to +/- 2,787 ft | 2 |  | 2015-02-26 19:00
2015-02-26 19:00 | Drill out plugs, baffle, shoe track cement and shoe | 2 |  | 2015-02-26 21:00
2015-02-26 21:00 | Drill out 10 ft of new formation to 2,847 ft . C&C mud. | 2.5 |  | 2015-02-26 23:30
2015-02-26 23:30 | Perform FIT on 13-3/8" shoe | 1.5 |  | 2015-02-27 01:00
2015-02-27 01:00 | POOH | 4 |  | 2015-02-27 05:00
2015-02-27 05:00 | Lay out 8" OD BHA | 4 |  | 2015-02-27 09:00
2015-02-27 09:00 | Rig Up SDC | 1 |  | 2015-02-27 10:00
2015-02-27 10:00 | Run 13-3/8" centroller gyro | 3 |  | 2015-02-27 13:00
2015-02-27 13:00 | Rig down | 0.5 |  | 2015-02-27 13:30
2015-02-27 13:30 | P/U & M/U 12-1/4" PDC Xceed BHA | 4.5 |  | 2015-02-27 18:00
2015-02-27 18:00 | RIH on 5" DP to ± 1,600 ft | 1 |  | 2015-02-27 19:00
2015-02-27 19:00 | Shallow test tools | 0.5 |  | 2015-02-27 19:30
2015-02-27 19:30 | RIH to 2,847 ft . Downlink Xceed | 1.5 |  | 2015-02-27 21:00
2015-02-27 21:00 | Drill 12-1/4" hole from 2,847 ft to 7,179 ft | 38 |  | 2015-03-01 11:00 |  | Based on Avg ROP of GD-02: 115 ft/hr
2015-03-01 11:00 | Flow chk, change gear Hi, TD survey | 1 |  | 2015-03-01 12:00
2015-03-01 12:00 | B/R OOH Hawar 7,179 ft to 5,866 ft 40 mins/std | 12 |  | 2015-03-02
2015-03-02 | B/R OOH Shuaiba from 5,866 ft to 4,075 ft 20 mins/std | 12 |  | 2015-03-02 12:00
2015-03-02 12:00 | B/R OOH NU from 4,075 ft to 3638 ft 40 mins/std | 8 |  | 2015-03-02 20:00
2015-03-02 20:00 | B/R OOH from 3,638 ft to 3,170 ft 20 mins/std | 5 |  | 2015-03-03 01:00
2015-03-03 01:00 | B/R OOH from 3,170 ft to shoe at 2,837 ft at 30 mins/std | 4 |  | 2015-03-03 05:00
2015-03-03 05:00 | Circ 1.5 Btms Up | 1 |  | 2015-03-03 06:00
2015-03-03 06:00 | Flow check. Service TDS. | 0.5 |  | 2015-03-03 06:30
2015-03-03 06:30 | B/R 5 stands for hole cleaning inside csg | 3 |  | 2015-03-03 09:30
2015-03-03 09:30 | Slug pipe POOH to surface | 4 |  | 2015-03-03 13:30
2015-03-03 13:30 | L/D jars and accelerator | 1 |  | 2015-03-03 14:30
2015-03-03 14:30 | L/D DC's, MWD, and RSS | 3 |  | 2015-03-03 17:30
2015-03-03 17:30 | Clear rig floor. | 0.5 |  | 2015-03-03 18:00
2015-03-03 18:00 | Pull Wear Bushing | 1 |  | 2015-03-03 19:00
2015-03-03 19:00 | P/U 2 stds HWDP, M/U test plug. Test 9-5/8" casing rams. L/O test plug. | 0 |  | 2015-03-03 19:00
2015-03-03 19:00 | Jet WH and BOP. | 1.5 |  | 2015-03-03 20:30
2015-03-03 20:30 | Run 9-5/8" casing |  |  | 2015-03-03 20:30
2015-03-03 20:30 | M/U 5 ft dp pup on casing fill up tool. L/O same. | 0.5 |  | 2015-03-03 21:00
2015-03-03 21:00 | R/U csg equipment | 3 |  | 2015-03-04
2015-03-04 | M/U 9-5/8" shoetrack | 1 |  | 2015-03-04 01:00
2015-03-04 01:00 | RIH 9-5/8" csg to 7,169 ft | 19 |  | 2015-03-04 20:00
2015-03-04 20:00 | R/U cmt head & HP lines | 0.5 |  | 2015-03-04 20:30
2015-03-04 20:30 | P/T surface lines | 0.5 |  | 2015-03-04 21:00
2015-03-04 21:00 | Rig pump lo rheology mud | 2.5 |  | 2015-03-04 23:30
2015-03-04 23:30 | Rig pump spacer, drop plug | 0.5 |  | 2015-03-05
2015-03-05 | Mix & pump cement | 3 |  | 2015-03-05 03:00
2015-03-05 03:00 | Displace & bump plug | 2 |  | 2015-03-05 05:00
2015-03-05 05:00 | P/T casing 3,000 psi | 0.5 |  | 2015-03-05 05:30
2015-03-05 05:30 | R/D cement lines and cmt head | 1.5 |  | 2015-03-05 07:00
2015-03-05 07:00 | Back out rng tool. POOH LD landing joints. | 1.5 |  | 2015-03-05 08:30
2015-03-05 08:30 | Rig down 9-5/8" casing rng and fill up tools. | 2.5 |  | 2015-03-05 11:00
2015-03-05 11:00 | M/U mill/flush tool. Flush riser, WH & BOP | 2 |  | 2015-03-05 13:00
2015-03-05 13:00 | Install & P-test MS-T seal | 2 |  | 2015-03-05 15:00
2015-03-05 15:00 | POOH seal rng tool. Inspect. OK. | 1.5 |  | 2015-03-05 16:30
2015-03-05 16:30 | P/u and check service break on CTT. L/O. | 0.5 |  | 2015-03-05 17:00
2015-03-05 17:00 | POOH and rack back HWDP. | 0.5 |  | 2015-03-05 17:30
2015-03-05 17:30 | Change 9-5/8" rams to blind rams | 2.5 |  | 2015-03-05 20:00
2015-03-05 20:00 | M/U test plug, full BOP test. | 6 |  | 2015-03-06 02:00
2015-03-06 02:00 | Make up CTT Test SOV to 3,500. POOH and L/O CTT. | 2 |  | 2015-03-06 04:00
2015-03-06 04:00 | Install short WB | 0.5 |  | 2015-03-06 04:30
2015-03-06 04:30 | Clear rig floor. | 1 |  | 2015-03-06 05:30
2015-03-06 05:30 | Drill 8-1/2" hole |  |  | 2015-03-06 05:30 |  | To be updated
2015-03-06 05:30 | Install PS21 | 0.5 |  | 2015-03-06 06:00
2015-03-06 06:00 | P/U & rack 219 jts 5" DP | 16 | 18 | 2015-03-07
2015-03-07 | M/U 8-1/2" BHA (Xceed 675 /Tele-/Stethp/Ecoscope) | 4 | 4 | 2015-03-07 04:00
2015-03-07 04:00 | Single in 59 stands with BHA | 10 | 13.5 | 2015-03-07 17:30
2015-03-07 17:30 | Service TDS. Set Torque sync. Calibrate depth sensors. | 1 | 1 | 2015-03-07 18:30
2015-03-07 18:30 | RIH, drill out cmt, displace to 9.5 ppg mud. | 3 | 5 | 2015-03-07 23:30
2015-03-07 23:30 | Drill 8-1/2" hole frm 8,744 ft to 11,600 ft | 23 | 23 | 2015-03-08 22:30
2015-03-08 22:30 | Drill 8-1/2" hole frm 11,600 ft to 16,190 ft | 24 | 24 | 2015-03-09 22:30
2015-03-09 22:30 | Drill 8-1/2" hole frm 16,190 ft to 18,923 ft | 24 | 16.5 | 2015-03-10 15:00
2015-03-10 15:00 | Drill 8-1/2" hole frm 18,923 ft to 19,768 ft | 3 | 2.5 | 2015-03-10 17:30
2015-03-10 17:30 | Drill 8-1/2" hole frm 19,768 ft to 20,670 ft | 20 | 21 | 2015-03-11 14:30
2015-03-11 14:30 | Drill 8-1/2" hole frm 20,670 ft to 23,800 ft TD | 16 | 18 | 2015-03-12 08:30
2015-03-12 08:30 | Flow check well. | 0.5 | 0.5 | 2015-03-12 09:00
2015-03-12 09:00 | Circ 2 x B/U while staging OOH frm 23,800 to 23,500 ft | 3.5 | 3.5 | 2015-03-12 12:30
2015-03-12 12:30 | B/R f/ 23,500 ft to shoe at 8,742 ft taking 2 caliper stations | 27 | 37 | 2015-03-14 01:30
2015-03-14 01:30 | Circ clean at 9-5/8" shoe, flow check | 1 | 1.5 | 2015-03-14 03:00
2015-03-14 03:00 | Service TDS. Drops inspection F/C well, | 1 | 1.5 | 2015-03-14 04:30
2015-03-14 04:30 | POOH laying down 31 stds, RIH 28 stds, POOH laying down 28 stds | 12 | 12 | 2015-03-14 16:30
2015-03-14 16:30 | POOH 5" DP to BHA | 5.5 | 5.5 | 2015-03-14 22:00
2015-03-14 22:00 | Reset WB recovered on BHA |  | 0.5 | 2015-03-14 22:30
2015-03-14 22:30 | L/D 8-1/2" Xceed BHA | 3 | 4 | 2015-03-15 02:30
2015-03-15 02:30 | Remove PS-21. Install master bushing. | 0.5 | 0.5 | 2015-03-15 03:00
2015-03-15 03:00 | Install 5" x 7" Liner # 1 |  |  | 2015-03-15 03:00
2015-03-15 03:00 | Clean and clear rig floor and PJSM | 0.5 | 1 | 2015-03-15 04:00 |  |  | Clean and clear rig floor
2015-03-15 04:00 | R/U 5" liner handling equipment and M/U bullnose | 1.5 | 1 | 2015-03-15 05:00 |  |  | R/U 5" liner handling equipment
2015-03-15 05:00 | RIH 5" 2,200 ft pre-drilled liner # 1 | 4 | 4 | 2015-03-15 09:00 |  |  | RIH 5" bullnose and 2,200 ft pre-drilled liner # 1
2015-03-15 09:00 | C/O to 7" equipt. Change PS21 to 7" | 1 | 1 | 2015-03-15 10:00 |  |  | C/O to 7" liner handling equipment
2015-03-15 10:00 | P/U 5" x 7" x/o, | 0.5 | 0.5 | 2015-03-15 10:30 |  |  | P/U 5" x 7" x/o, 1 joint pre-drilled 7", Resman tracer joint,
2015-03-15 10:30 | PJSM with crew coming on shift | 0.5 | 0.5 | 2015-03-15 11:00
2015-03-15 11:00 | RIH 7" x 2,400 ft pre-drilled liner # 1 | 4 | 5 | 2015-03-15 16:00
2015-03-15 16:00 | P/U Resman tracer joint | 0.5 | 0.5 | 2015-03-15 16:30
2015-03-15 16:30 | C/O to 5" DP equipment | 0.5 | 0.5 | 2015-03-15 17:00
2015-03-15 17:00 | M/U liner setting sleeve / PBR | 1 | 0.5 | 2015-03-15 17:30
2015-03-15 17:30 | RIH 5 x 7" liner # 1 on 5" DP to ± 17,300 ft | 7 | 10 | 2015-03-16 03:30
2015-03-16 03:30 | Dry Ream from +/- 17,300 ft to ± 23,800 ft, | 26 | 14 | 2015-03-16 17:30
2015-03-16 17:30 | Drop setting ball & release liner | 2 | 1 | 2015-03-16 18:30 |  |  | RIH 5 x 7" liner # 1 on 5" DP to ± 10,000 ft
2015-03-16 18:30 | Flowcheck well | 0.5 |  | 2015-03-16 19:00 |  |  | Dry Ream from 10,000 ft to ± 23,799 ft,
2015-03-16 19:00 | B/R OOH 3 stds |  | 0.5 | 2015-03-16 19:30 |  |  | Drop setting ball & release liner
2015-03-16 19:30 | F/C well, POOH 5 stds wet |  | 1.5 | 2015-03-16 21:00
2015-03-16 21:00 | POOH to 9-5/8" shoe |  | 15.5 | 2015-03-17 12:30
2015-03-17 12:30 | Slip & Cut Drilling Line | 1.5 |  | 2015-03-17 14:00
2015-03-17 14:00 | F/C well, POOH to surface | 7 | 5.5 | 2015-03-17 19:30 |  |  | Flowcheck well
2015-03-17 19:30 | L/O Liner # 1 running tool | 1 | 0.5 | 2015-03-17 20:00 |  |  | B/R OOH from 17,224 ft to 9-5/8" shoe at 8,742 ft
2015-03-17 20:00 | Install 7" Liner # 2 |  |  | 2015-03-17 20:00
2015-03-17 20:00 | C/O to 7" liner equipment, PJSM | 1 | 1.5 | 2015-03-17 21:30
2015-03-17 21:30 | RIH 7" liner # 2 P/U seal stem | 1 | 0.5 | 2015-03-17 22:00
2015-03-17 22:00 | RIH 200 ft of 7" BLANK liner #2 | 0.5 |  | 2015-03-17 22:30
2015-03-17 22:30 | PJSM, P/U MPas & Swell pkr, | 2 | 1 | 2015-03-17 23:30
2015-03-17 23:30 | RIH 200 ft of 7" BLANK liner #2 |  | 0.5 | 2015-03-18
2015-03-18 | P/U Baker PBR and RIH |  | 0.5 | 2015-03-18 00:30
2015-03-18 00:30 | RIH 2,400 ft pre-drilled 7" liner | 4.5 |  | 2015-03-18 05:00
2015-03-18 05:00 | C/O to 5" DP equipment | 0.5 |  | 2015-03-18 05:30
2015-03-18 05:30 | M/U liner setting sleeve / PBR | 1 |  | 2015-03-18 06:30
2015-03-18 06:30 | RIH 7" liner # 2 on 5" DP to ± 17,650 ft | 8 | 11.5 | 2015-03-18 18:00
2015-03-18 18:00 | Dry Ream from ± 17,650 ft to ± 19,168 ft | 17.5 | 3.5 | 2015-03-18 21:30
2015-03-18 21:30 | Sting in, drop setting ball & release liner | 2 | 1.5 | 2015-03-18 23:00
2015-03-18 23:00 | B/R 3 stds, F/C well | 1.5 |  | 2015-03-19 00:30
2015-03-19 00:30 | POOH from ± 16,236 ft to 9-5/8" shoe | 9 |  | 2015-03-19 09:30
2015-03-19 09:30 | F/C well, POOH to surface | 5 |  | 2015-03-19 14:30
2015-03-19 14:30 | L/O Liner # 2 running tool | 1 |  | 2015-03-19 15:30
2015-03-19 15:30 | Install 7" Liner # 3 |  |  | 2015-03-19 15:30
2015-03-19 15:30 | C/O to 7" liner equipment | 1 |  | 2015-03-19 16:30
2015-03-19 16:30 | PJSM, RIH 7" liner # 3 p/u seal stem to PBR | 1 |  | 2015-03-19 17:30
2015-03-19 17:30 | RIH 4,725 ft pre-drilled 7" liner #3 | 7.5 | 8.5 | 2015-03-20 02:00
2015-03-20 02:00 | C/O to 5" DP equipment | 1 |  | 2015-03-20 03:00
2015-03-20 03:00 | M/U liner setting sleeve / PBR | 1 |  | 2015-03-20 04:00
2015-03-20 04:00 | RIH 7" liner # 3 on 5" DP to ± 16,100 ft | 9 |  | 2015-03-20 13:00
2015-03-20 13:00 | Dry Ream from ± 10,000 ft to ± 16,234 ft, sting in | 0 |  | 2015-03-20 13:00
2015-03-20 13:00 | Drop setting ball & release liner | 2 |  | 2015-03-20 15:00
2015-03-20 15:00 | B/R from 11,484 ft to 9-5/8" shoe at 8,742 ft | 4 |  | 2015-03-20 19:00
2015-03-20 19:00 | F/C well, POOH to surface | 5 |  | 2015-03-21
2015-03-21 | L/O Liner # 3 running tool | 1 |  | 2015-03-21 01:00
2015-03-21 01:00 | Install 7" Liner # 4 |  |  | 2015-03-21 01:00
2015-03-21 01:00 | C/O to 7" liner equipment | 1 |  | 2015-03-21 02:00
2015-03-21 02:00 | RIH 7" liner # 4 p/u seal stem to PBR | 1 |  | 2015-03-21 03:00
2015-03-21 03:00 | RIH 1,500 ft pre-drilled 7" liner # 4 | 2.5 |  | 2015-03-21 05:30
2015-03-21 05:30 | P/U Resman tracer and 200 ft BLANK liner, Mpas and Swell packers | 2 |  | 2015-03-21 07:30
2015-03-21 07:30 | RIH 280 ft BLANK liner, 600 ft pre-drilled liner, P/U Resman tracer, 160 ft BLANK liner | 2 |  | 2015-03-21 09:30
2015-03-21 09:30 | C/O to 5" DP equipment | 0.5 |  | 2015-03-21 10:00
2015-03-21 10:00 | M/U liner hanger assy | 1 |  | 2015-03-21 11:00
2015-03-21 11:00 | RIH 7" liner # 4 on 5" DP to ± 10,000 ft | 7 |  | 2015-03-21 18:00
2015-03-21 18:00 | P/U 5 stds HWDP and 21 singles of HWDP | 2.5 |  | 2015-03-21 20:30
2015-03-21 20:30 | RIH 7" liner # 4 on 5" DP to ± 11,484 ft | 1 |  | 2015-03-21 21:30
2015-03-21 21:30 | Sting in, Drop ball, Set liner top packer and release RT | 2 |  | 2015-03-21 23:30
2015-03-21 23:30 | Circ hole clean above TOL, flow check | 1.5 |  | 2015-03-22 01:00
2015-03-22 01:00 | F/C well, POOH to surface | 7 |  | 2015-03-22 08:00
2015-03-22 08:00 | L/O Liner Hanger running tool | 1 |  | 2015-03-22 09:00
2015-03-22 09:00 | 7" x 9-5/8" Cleanout |  |  | 2015-03-22 09:00
2015-03-22 09:00 | C/O to 4" DP handling equipment | 0.5 |  | 2015-03-22 09:30
2015-03-22 09:30 | M/U 6" bit on 7" scraper BHA | 2.5 |  | 2015-03-22 12:00
2015-03-22 12:00 | Pick up 16 stds of 4" DP | 3.5 |  | 2015-03-22 15:30
2015-03-22 15:30 | C/O to 5" DP equipment | 0.5 |  | 2015-03-22 16:00
2015-03-22 16:00 | P/U 9-5/8" scraper BHA | 1.5 |  | 2015-03-22 17:30
2015-03-22 17:30 | RIH 7" x 9-5/8" clean out assy to 9,511 ft Tag swell packer. | 6 |  | 2015-03-22 23:30
2015-03-22 17:30 | Scrape pkr setting intervals 8,006 ft and 9,511 ft | 1 |  | 2015-03-22 18:30
2015-03-22 18:30 | POOH R/B 5" DP | 3.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | L/D 9-5/8" scraper BHA | 1.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | C/O to 4" DP handling equipment | 0.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | POOH & Rack back 12 stds 4" dp, L/D 4 stds 4" DP | 3 |  | 2015-03-22 18:30
2015-03-22 18:30 | L/D 7" scraper BHA | 1.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | Pull WB and jet WH & BOP | 2.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | Full BOP test (Last test: 24-01-15) | 6 |  | 2015-03-22 18:30
2015-03-22 18:30 | RE set WB | 0.5 |  | 2015-03-22 18:30
2015-03-22 18:30 | Completion |  |  | 2015-03-22 18:30
2015-03-22 18:30 | Install spreader and sheaves in mast | 2.5 |  | 2015-03-22 21:00
2015-03-22 18:30 | R/U 3-1/2" handling equipment | 2 |  | 2015-03-22 20:30
2015-03-22 20:30 | P/U & M/U anchor seal assy on 1 jt 3-1/2 tbg | 0.5 |  | 2015-03-22 21:00
2015-03-22 21:00 | P/U & M/U and RIH 9,000 ft 3 1/2" tbg. Fill tbg every 10 joints | 20 |  | 2015-03-23 17:00
2015-03-23 17:00 | Install X/O and Petrowell Latch assy | 0.5 |  | 2015-03-23 17:30
2015-03-23 17:30 | Change to 4" dp handling eq. Install Schlumberger Swivel | 0.5 |  | 2015-03-23 18:00
2015-03-23 18:00 | RIH lower completion on +- 12 stds 4" DP | 1.5 |  | 2015-03-23 19:30
2015-03-23 19:30 | Change to 5" DP and RIH to setting depth 18,663 ft (90 stds) | 10 |  | 2015-03-24 05:30
2015-03-24 05:30 | Sting in and shear out Petrowell latch | 1 |  | 2015-03-24 06:30
2015-03-24 06:30 | Displace to Brine/SGA II | 2 |  | 2015-03-24 08:30
2015-03-24 08:30 | POOH to TOL | 1 |  | 2015-03-24 09:30
2015-03-24 09:30 | Displace to Completion Fluid | 1 |  | 2015-03-24 10:30
2015-03-24 10:30 | POOH L/D 4" DP | 9 |  | 2015-03-24 19:30
2015-03-24 19:30 | Pull WB and jet wehead with Multi-task filter | 2 |  | 2015-03-24 21:30
2015-03-24 21:30 | Re-test Annular seal to 5,000 psi. | 0.5 |  | 2015-03-24 22:00
2015-03-24 22:00 | PJSM R/U to run 4 1/2" completion assy. | 1.5 |  | 2015-03-24 23:30
2015-03-24 23:30 | C/O elevator to 3 1/2" | 0.5 |  | 2015-03-25
2015-03-25 | P/U & M/U ROC, LVO, X/O, HS-IVC | 3 |  | 2015-03-25 03:00
2015-03-25 03:00 | P/U & M/U 1 jt x 3-1/2 tbg, 7" MFT pkr, x/o | 2 |  | 2015-03-25 05:00
2015-03-25 05:00 | Change to 4 1/2 " RIH 1,400 ft 4-1/2" completion | 5 |  | 2015-03-25 10:00
2015-03-25 10:00 | P/U & M/U sliding sleeve and Inj sub | 2.5 |  | 2015-03-25 12:30
2015-03-25 12:30 | M/U 9-5/8" MFR pkr , terminate C/L's | 9 |  | 2015-03-25 21:30
2015-03-25 21:30 | RIH 5,250 ft 4-1/2" completion | 17 |  | 2015-03-26 14:30
2015-03-26 14:30 | P/U & M/U 1 jt 4-1/2" tbg, SPM | 1 |  | 2015-03-26 15:30
2015-03-26 15:30 | RIH 750 ft 4-1/2" completion | 3 |  | 2015-03-26 18:30
2015-03-26 18:30 | P/U & M/U TRMAXX SSSV | 1 |  | 2015-03-26 19:30
2015-03-26 19:30 | RIH 1,890 ft 4-1/2" completion | 7 |  | 2015-03-27 02:30
2015-03-27 02:30 | M/U x/o with 2 stds DP | 0.5 |  | 2015-03-27 03:00
2015-03-27 03:00 | Sting in and Space out | 4 |  | 2015-03-27 07:00
2015-03-27 07:00 | P/U tbg hanger, feed C/L through hgr | 7 |  | 2015-03-27 14:00
2015-03-27 14:00 | Install comms collar & seal assy | 3.5 |  | 2015-03-27 17:30
2015-03-27 17:30 | Function test SSSV | 0.5 |  | 2015-03-27 18:00
2015-03-27 18:00 | Land hanger, P/T annular seal, O/P test | 3.5 |  | 2015-03-27 21:30
2015-03-27 21:30 | Set 9-5/8" MFR and MFT pkrs, P/T tbg | 1 |  | 2015-03-27 22:30
2015-03-27 22:30 | Inflow test SSSV, P/T C Section | 1.5 |  | 2015-03-28
2015-03-28 | Shear GLV, inflow test GLV | 1 |  | 2015-03-28 01:00
2015-03-28 01:00 | R/U Sline, install CRQ/DBSS, P/T, R/D Sline | 4.5 |  | 2015-03-28 05:30
2015-03-28 05:30 | L/D 7" landing string, clear rig floor | 1 |  | 2015-03-28 06:30
2015-03-28 06:30 | Heavy Lift - N/D Bell Nipple, BOP & Riser | 5 |  | 2015-03-28 11:30
2015-03-28 11:30 | Remove comms collar, terminate C/L's, install hgr neck seal | 5.5 |  | 2015-03-28 17:00
2015-03-28 17:00 | Heavy lift - Install XMT | 4 |  | 2015-03-28 21:00
2015-03-28 21:00 | P/T XMT void, hgr neck seal & body | 3 |  | 2015-03-29
2015-03-29 | R/U Sline & PCE, retrieve CRQ/DBSS, R/D Sline & PCE | 5 |  | 2015-03-29 05:00
2015-03-29 05:00 | Shear chem inj burst disc. Pump 30 bbls. | 1 |  | 2015-03-29 06:00
2015-03-29 06:00 | Prepare & skid to GD-21 | 2 |  | 2015-03-29 08:00
Formulas:
Rig Name = [End, row above]
Rig Name = IF([ACT, row above]>0,[Rig Name, row above]+[ACT, row above]/24,[Rig Name, row above]+[Start Date, row above]/24)
End = IF(ISBLANK([ACT]),+[Rig Name]+[Start Date]/24,+[Rig Name]+[ACT]/24)
End = IF(ISBLANK([ACT]),+[Rig Name]+K253/24,+[Rig Name]+[ACT]/24)